## README
2018-11-07
Author | Kau Chung
Email | kchun014@ucr.edu
Description | Scrum Sheets for Dynamiq Zynergi Recipe Binder project.
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means by "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Minimize task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
1 | Login/Logout | As a person interested in Recipe Binder, I want to register for an account so that I may login/logout to my own personal account. | 6 | 1
2 | Recipes | As a registered user, I want to be able to create a recipe and share it with the rest of the community | 4 | 2 | Recipes can be stored in database
3 | Favorite Recipes | As a registered user, I want to keep a list of my favorite recipes that I can save and view whenever I want. | 4 | 5
4 | Favorite Cooks | As a registered user, I want to keep a list of my favorite cooks, so that I may see their recipes | 2 | 4
5 | Comment | As a registered user, I want to comment on other registered users' recipes to give feedback on a recipe's merits. | 3 | 5
6 | Password Update | As a registered user, I want to edit my own password whenever I feel necessary. | 6 | 5
7 | Google API | As an unregistered user, I want to use a personal Google account to login the app, so I do not have to create a new account. | 6 | 2
8 | Profile | As a registered user, I should be able to look at my followers, look at people I am following, view my recipes, and view recipes I favorited so that I can access recipes important to me. | 7 | 1
9 | Delete Account | As a registered account, I should be able to delete my account, so that I can safely remove my information from the app | 2 | 5
10 | Ingredient Substitutions | As a user, I want to be able to learn about substitutes to a given ingredient for vegans, vegetarians, allergies | 4 | 4
11 | Recipe Feed | As a registered user, I want to be able to see a feed of recipes posted by favorite cooks to discover new recipes | 10 | 2 | To be split into several tasks
| Total |  | 54
Cancelled

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
Task 8: Create Feed UI(Carlos and Jake) | Task 13: Create Post UI(Carlos Gomez) | Task 4: Implement User Class(Kau Chung)
Task 10: Figuring out how we are going to create our unique IDs(Parsakon Homvech) | Task 15: Link Sign Up with Account Setup (Emily Huang) | Task 9: Create Profile UI(Carlos Gomez)
Task 11: Create a splash screen(Parsakon Homvech) | Task 16: Profile Settings (Emily Huang) | Task 1: Create/Implement Post Object(Jake Kuznicki)
Task 17: Figure out implementation for substitutions (Kau Chung) |  | Task 5: Create/Implement Comment Object(Jake Kuznicki)

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | Parsakon Homvech | Task 3: Login Page(Parsakon Homvech)
1 | Parsakon Homvech | Task 2: Create Recipe Class(Carlos Gomez)
1 | Parsakon Homvech | Task 12: Create Recipe UI(Kau Chung)
1 | Parsakon Homvech | Task 7: Firebase Database(Emily Huang)
1 | Parsakon Homvech | Task 6: Account Setup(Emily Huang)
1 | Parsakon Homvech | Task 14: Create a Recipe(Parsakon Homvech)

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 42 | 7 | 0 | 42 | 42
1 | 42 | 10 | 10 | 32 | 36.75
2 | 42 | 8 | 18 | 24 | 31.5
3 | 42 | 3 | 21 | 21 | 26.25
4 | 42 | 4 | 25 | 17 | 21
5 | 42 | 3 | 28 | 14 | 15.75
6 | 42 | 6 | 34 | 8 | 10.5
7 |  |  |  |  | 5.25
8 |  |  |  |  | 0